## Sheet1
Feature | FE-07_Filter and Toggle Map Layers | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | 15 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 13 | 0 | 0 | 0
Round 2 | 0 | 0 | 0 | 0
Round 3 | 0 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Map Layers
TC-1 | Verify Layer Toggle Sheet opens and displays options. | 1. Navigate to Map tab. 2. Tap the Layers button (in MapHeader or MapControls). 3. Observe the LayerToggleSheet that appears. | System displays LayerToggleSheet with: Base map options (Standard/Satellite). Overlay toggles: (Flood) and (Traffic) and (Weather). Opacity sliders for applicable layers. | User is logged into the FDA App. Map tab is open. | Passed | 2026-01-21 | PhucTNH | [6 empty] | Layer toggle sheet
TC-2 | Verify toggling Flood layer shows/hides flood markers. | 1. Navigate to Map tab. 2. Open Layer Toggle Sheet. 3. Toggle OFF the Flood layer. 4. Observe the map. 5. Toggle ON the Flood layer. 6. Observe the map. | When Flood layer is OFF: FloodSeverityMarkers are hidden and no station pins visible. When Flood layer is ON: FloodSeverityMarkers are visible and station pins appear with severity colors. | User is logged into the FDA App. Layer Toggle Sheet is open. | Passed | 2026-01-22 | PhucTNH | [6 empty] | Flood layer toggle
TC-3 | Verify toggling Traffic layer shows/hides traffic overlay. | 1. Navigate to Map tab. 2. Open Layer Toggle Sheet. 3. Toggle ON the Traffic layer. 4. Observe the map. 5. Toggle OFF the Traffic layer. | When Traffic layer is ON: showsTraffic=true and traffic colors (green/yellow/red) appear on roads. Custom map style is disabled to show default road colors. When Traffic layer is OFF: traffic overlay is hidden. | User is logged into the FDA App. Layer Toggle Sheet is open. | Passed | 2026-01-23 | PhucTNH | [6 empty] | Traffic layer toggle
TC-4 | Verify changing base map between Standard and Satellite. | 1. Navigate to Map tab. 2. Open Layer Toggle Sheet or use MapHeader toggle. 3. Select Satellite base map. 4. Observe the map. 5. Select Standard base map. | Map displays satellite imagery when Satellite is selected. Map displays standard road/terrain view when Standard is selected. Map type change is animated/smooth. | User is logged into the FDA App. Map tab is open. | Passed | 2026-01-24 | PhucTNH | [6 empty] | Base map toggle
TC-5 | Verify Layer settings are saved and persist across sessions. | 1. Navigate to Map tab. 2. Open Layer Toggle Sheet. 3. Change layer settings (e.g. enable Traffic and disable Flood). 4. Close the app completely. 5. Reopen the app and navigate to Map tab. 6. Open Layer Toggle Sheet. | Layer settings (baseMap and overlays and opacity) are persisted via Redux state and API. On reopen: settings match the previously saved values. saveMapSettings is called with debounce when settings change. | User is logged into the FDA App. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Settings persistence
Street View
TC-1 | Verify long press on map sets Street View marker. | 1. Navigate to Map tab. 2. Long press on any location on the map. 3. Observe the map. | System places a Street View marker (orange eye icon) at the long-pressed location. Hint text " Street View" appears. | User is logged into the FDA App. Map tab is open. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Street View marker
TC-2 | Verify tapping Street View marker opens Street View. | 1. Navigate to Map tab. 2. Long press on map to set Street View marker. 3. Tap on the orange Street View marker. | System calls openStreetView with marker coordinates. External Google Street View or in-app Street View is launched showing the location. | User is logged into the FDA App. Street View marker is set. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Open Street View
TC-3 | Verify clearing Street View marker. | 1. Navigate to Map tab. 2. Set a Street View marker via long press. 3. Use the clear Street View button in MapControls (if visible). 4. Observe the map. | Street View marker is removed from map. Hint text disappears. streetViewLocation is set to null. | User is logged into the FDA App. Street View marker is set. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Clear Street View
Real-time Data
TC-1 | Verify flood markers refresh when panning map. | 1. Navigate to Map tab with Flood layer enabled. 2. Pan the map to a new viewport area. 3. Wait approximately 1 second (debounce time). 4. Observe markers loading. | System calls refreshFloodSeverity with new viewport bounds (minLat and maxLat and minLng and maxLng). New flood severity markers appear for stations within the new viewport. API call is debounced to 1000ms to prevent excessive calls. | User is logged into the FDA App. Flood layer is enabled. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Viewport-based refresh
TC-2 | Verify markers show real-time water level data. | 1. Navigate to Map tab. 2. Tap on a flood severity marker. 3. Observe the water level value in FloodStationCard. 4. Check measuredAt timestamp. | FloodStationCard displays current waterLevel from API. measuredAt shows recent timestamp (formatted in Vietnamese locale). Unit is correctly displayed (cm/m). | User is logged into the FDA App. Stations have recent data. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Real-time water level
TC-3 | Verify station status indicator (Active/Inactive). | 1. Navigate to Map tab. 2. Tap on different flood severity markers. 3. Observe the station status in FloodStationCard footer. | System shows station status indicator: Green dot + for active stations. Red dot + for inactive stations. Status is based on stationStatus property from API. | User is logged into the FDA App. Map tab is open. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Station status display
TC-4 | Verify handling of stations with missing data. | 1. Navigate to Map tab. 2. Find a station with incomplete data (null values). 3. Tap on the marker. 4. Observe the FloodStationCard display. | System handles null values gracefully: waterLevel shows ""N/A"" if null. measuredAt shows if null. Optional fields (sensorHeight and distance and roadName and locationDesc) are hidden if null. Marker uses ""unknown"" severity color (gray) if severity cannot be determined. | User is logged into the FDA App. Station with incomplete data exists. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Handle missing data
TC-5 | Verify loading state during initial data fetch. | 1. Clear app cache/data. 2. Login and navigate to Map tab immediately. 3. Observe the loading behavior. | MapLoadingOverlay is displayed while map is loading (isLoading=true). Flood markers show loading state (floodLoading) while fetching. Once data loads and loading overlay disappears and markers appear. | User has just logged in. App cache may be cleared. | Passed | 2026-01-25 | PhucTNH | [6 empty] | Loading state