## FE-15
Feature | FE-15_View Flood Alert History | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View Alert History List
TC-01 | Verify Alert History — Happy Path. | 1. Log in. 2. Navigate to Alert History. 3. Wait for list to load. | HTTP 200 OK. List displayed with station name, severity, water level, timestamp, and status (Open/Resolved). | User authenticated. Data exists. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-02 | Verify Alert History — Empty State. | 1. Login with account having no history. 2. Navigate to Alert History. | HTTP 200 OK. Empty array returned. UI shows 'No alert history found'. | No alerts exist. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-03 | Verify Card Displays All Required Fields. | 1. Inspect alert card. 2. Cross-check with API. | Correctly displays: station name/code, severity badge, water level (cm), message, triggeredAt, status, and notification list. | Data exists. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-04 | Verify Loading State. | 1. Open screen. 2. Observe fetch. | Loading indicator or skeleton screen is shown during fetch. | None. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-05 | Open alerts at top. | 1. Observe list order. | Open (unresolved) alerts are displayed first. | Both open and resolved alerts exist. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-06 | resolvedAt timestamp. | 1. Locate resolved alert card. | Shows correct resolvedAt timestamp in local timezone. | Resolved alert exists. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-07 | Notification channel icons. | 1. Inspect notification list on card. | Icons for Push, Email, SMS shown correctly with status (sent/failed). | Alerts with multiple channels exist. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-08 | Water level unit (cm). | 1. Check water level field. | Displayed with unit 'cm' (e.g., '250 cm'). Consistent across cards. | Data exists. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-09 | Pull-to-refresh. | 1. Pull down to refresh. | Indicator appears. List updated with latest alerts. | None. | Passed | 2026-03-05 | HuyDQ | Passed | 2026-04-04 | HuyDQ
Filtering
TC-01 | Filter by Area ID. | 1. Apply areaId filter. | HTTP 200 OK. Only alerts from specific area shown. | Multiple areas exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-02 | Filter by Severity 'caution'. | 1. Filter severity='caution'. | Only 'caution' alerts shown. | Multiple severities exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-03 | Filter by Severity 'warning'. | 1. Filter severity='warning'. | Only 'warning' alerts shown. | Multiple severities exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-04 | Filter by Severity 'critical'. | 1. Filter severity='critical'. | Only 'critical' alerts shown. | Multiple severities exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-05 | Filter by fromDate. | 1. Set fromDate=2026-01-01. | Alerts triggeredAt >= 2026-01-01. | Data exists. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-06 | Filter by toDate. | 1. Set toDate=2026-01-31. | Alerts triggeredAt <= 2026-01-31. | Data exists. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-07 | Combined Filters. | 1. areaId + severity + date range. | Satisfies all criteria simultaneously. | Match exists. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-08 | No Results. | 1. Filter 'critical' in safe date range. | Empty array. UI shows 'No alerts found'. | No match. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-09 | Filter Status 'Open'. | 1. Filter status='open'. | Only open alerts shown. | Both statuses exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-10 | Filter Status 'Resolved'. | 1. Filter status='resolved'. | Only resolved alerts shown. | Both statuses exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-11 | Clear All Filters. | 1. Clear multiple filters. | Full list restored. | Filters applied. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-12 | Invalid areaId. | 1. Filter non-existent GUID. | HTTP 200 OK. Empty list. UI 'No alerts found'. | None. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
Pagination
TC-01 | Default Pagination. | 1. No params. | pageNumber=1, pageSize=10. Max 10 items. | 10+ alerts exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-02 | Load Next Page. | 1. Navigate to page 2. | Page 2 loaded and appended. pageNumber=2. | 10+ alerts exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-03 | Custom pageSize=20. | 1. Set pageSize=20. | 20 items returned per page. | 20+ alerts exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-04 | Last page hide 'Load More'. | 1. Go to last page. | Load More' button hidden/disabled. | All pages loaded. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-05 | Previous page. | 1. Back to page 1 from 2. | Page 1 loaded correctly. | 2+ pages exist. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ
TC-06 | Out of range. | 1. pageNumber=999. | HTTP 200 OK. Empty list. UI 'No alerts found'. | Fewer than 999 pages. | Passed | 2026-05-03 | HuyDQ | Passed | 2026-04-04 | HuyDQ

## FE-25
Feature | FE-25_Report Flood Points (Photo / Video) | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Create Report - Basic Submission
TC-01 | Submit report with valid latitude/longitude only (no media). | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Select valid location (lat/lng in range). 4. Leave description/media empty. 5. Submit report. | HTTP 201 Created. Response contains id, score=1, status=Published, createdAt. | Authenticated user. Stable network.
TC-02 | Submit report with valid description + 1 photo. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Enter valid description. 4. Attach 1 valid photo (.jpg/.jpeg/.png/.webp). 5. Submit report. | HTTP 201 Created. Report saved with photo reference. status=Published, score=1. | Authenticated user. Photo size <= 20MB.
TC-03 | Submit report with valid description + 1 video. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Enter valid description. 4. Attach 1 valid video (.mp4/.mov/.avi). 5. Submit report. | HTTP 201 Created. Report saved with video reference. status=Published, score=1. | Authenticated user. Video size <= 200MB.
TC-04 | Submit report with max photo count (5 photos). | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach exactly 5 valid photos. 4. Submit report. | HTTP 201 Created. Report accepted with all 5 photos. | Authenticated user.
TC-05 | Submit report with max video count (5 videos). | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach exactly 5 valid videos. 4. Submit report. | HTTP 201 Created. Report accepted with all 5 videos. | Authenticated user.
TC-06 | Reject unauthenticated request to create report. | 1. Sign out or remove access token. 2. Open Report Flood Point screen. 3. Submit valid report payload. | HTTP 401 Unauthorized (or auth failure response). Report is not created. | No valid authentication token.
TC-07 | Reject invalid latitude/longitude range. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Set latitude outside [-90,90] or longitude outside [-180,180]. 4. Submit report. | Validation error is returned. Report is not created. | Authenticated user.
TC-08 | Submit report with optional empty description. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Keep description empty and submit valid location. | HTTP 201 Created. Report is created successfully. | Authenticated user.
TC-09 | Verify success response contains minimum required fields. | 1. Log in with a valid account. 2. Submit a valid report. 3. Inspect response body. | Response contains id, score, status, createdAt. | Authenticated user. API inspection tool available.
Media Validation & Limits
TC-01 | Reject photo count exceeds limit (>5). | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach 6 valid photos and submit. | Validation error for photo count. Report is not created. | Authenticated user.
TC-02 | Reject video count exceeds limit (>5). | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach 6 valid videos and submit. | Validation error for video count. Report is not created. | Authenticated user.
TC-03 | Reject unsupported photo extension. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach unsupported photo type (e.g., .gif/.bmp) and submit. | Validation error for photo extension. Report is not created. | Authenticated user.
TC-04 | Reject unsupported video extension. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach unsupported video type (e.g., .mkv/.wmv) and submit. | Validation error for video extension. Report is not created. | Authenticated user.
TC-05 | Boundary: photo size exactly 20MB is accepted. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach one photo exactly 20MB and submit. | HTTP 201 Created. Report is accepted. | Authenticated user. Exact-size test file prepared.
TC-06 | Reject photo size greater than 20MB. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach one photo larger than 20MB and submit. | Validation error for photo size. Report is not created. | Authenticated user.
TC-07 | Boundary: video size exactly 200MB is accepted. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach one video exactly 200MB and submit. | HTTP 201 Created. Report is accepted. | Authenticated user. Exact-size test file prepared.
TC-08 | Reject video size greater than 200MB. | 1. Log in with a valid account. 2. Open Report Flood Point screen. 3. Attach one video larger than 200MB and submit. | Validation error for video size. Report is not created. | Authenticated user.
TC-09 | Verify response includes mediaLimits metadata. | 1. Log in with a valid account. 2. Submit a valid report. 3. Inspect mediaLimits object in response. | Response contains maxPhotoCount, maxVideoCount, maxPhotoSizeBytes, maxVideoSizeBytes, and allowed extensions. | Authenticated user.
Anti-spam & Visibility Rules
TC-01 | Cooldown anti-spam rejects second report within 3 minutes. | 1. Submit first valid report successfully. 2. Within 3 minutes, submit second valid report from same account. | Second request returns HTTP 429 with message and retryAfterSeconds. | Authenticated user. First report exists.
TC-02 | Coordinate burst marks new report as Hidden when nearby count >3 in 50m/10m. | 1. Prepare at least 4 recent reports in same area (within 50m, 10 minutes). 2. Submit another valid report at same coordinate cluster. | HTTP 201 Created. New report status=Hidden and score=1. | Controlled nearby dataset prepared.

## FE-26
Feature | FE-26_View Community Flood Reports | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Community Feed - Core Behavior
TC-01 | View community feed with authenticated user. | 1. Log in with a valid account. 2. Open Community Flood Reports screen. 3. Wait for initial feed request to complete. | HTTP 200 OK. Feed data is loaded and rendered. | Authenticated user. Stable network.
TC-02 | Community feed returns only Published reports. | 1. Log in with test account. 2. Open Community Flood Reports screen. 3. Compare response with dataset containing Published and Hidden records. | Only status=Published reports are returned. Hidden reports are excluded. | Dataset includes Published and Hidden records.
TC-03 | Community feed excludes reports below score threshold. | 1. Log in and open Community Flood Reports screen. 2. Trigger feed API and inspect items. 3. Compare with mixed-score dataset. | Returned list includes only reports with score >= minScore threshold. | Dataset includes low and high score reports.
TC-04 | Community feed sort order is newest first. | 1. Log in with a valid account. 2. Open Community Flood Reports screen. 3. Verify createdAt order of returned items. | Reports are ordered by createdAt DESC. | Dataset has multiple timestamps.
TC-05 | Apply bounds filter to map viewport. | 1. Log in and open map view. 2. Set bounds (minLat,minLng,maxLat,maxLng). 3. Load community feed for this viewport. | All returned reports are within the provided bounds. | Known dataset inside and outside bounds.
TC-06 | Default fromHours when omitted is applied. | 1. Log in with a valid account. 2. Call community feed without fromHours. 3. Inspect returned createdAt range. | System applies default fromHours=24. | Dataset includes old and recent records.
TC-07 | Custom fromHours filters correctly. | 1. Log in with a valid account. 2. Request community feed with fromHours=2. 3. Inspect createdAt fields. | Only reports from the last 2 hours are returned. | Dataset spans multiple hours.
TC-08 | minScore override query works. | 1. Log in and request feed with minScore=2. 2. Inspect score values in response. | All returned reports satisfy score >= 2. | Dataset includes scores below and above 2.
TC-09 | Pagination returns correct page slices. | 1. Log in and request page=1,pageSize=10. 2. Request page=2,pageSize=10. 3. Compare item overlap. | Each page has up to 10 items and page slices do not duplicate unexpectedly. | At least 20 matching records exist.
Nearby Query & Consensus
TC-01 | Feed response contains minimum required fields. | 1. Log in and load community feed. 2. Inspect one response item. 3. Verify mandatory fields. | Each item has id, latitude, longitude, description, score, createdAt; optional mediaPreview/votes may appear. | Authenticated user.
TC-02 | Nearby endpoint returns results around real GPS coordinate. | 1. Log in with a valid account. 2. Send POST /flood-reports/nearby with real device latitude/longitude, radiusMeters=5000, hours=24. 3. Inspect response list. | HTTP 200 OK. Nearby reports match distance/time filtering. | Test in area with known reports.
TC-03 | Nearby endpoint with coordinate (1,1) returns empty or no relevant data. | 1. Log in with a valid account. 2. Send nearby request with latitude=1 and longitude=1. 3. Inspect response payload. | HTTP 200 OK with empty result (or no relevant items). | No seeded reports near (1,1).
TC-04 | Nearby endpoint filters by Published and score >=0. | 1. Log in and call nearby endpoint with valid coordinate. 2. Compare response with mixed status/score dataset. | Only Published reports with score >=0 are returned. | Mixed dataset prepared in same radius.
TC-05 | Nearby with hours=0 returns all-time records in radius. | 1. Log in with a valid account. 2. Call nearby endpoint with hours=0. 3. Compare with historical records in same radius. | All-time records in radius are included, while status/score rules still apply. | Historical data exists.
TC-06 | Nearby default values for missing/invalid radius and hours. | 1. Log in with a valid account. 2. Call nearby endpoint without radiusMeters/hours or with invalid <=0 values. 3. Inspect applied behavior. | System applies default radiusMeters=500 and hours=2. | API defaulting behavior enabled.
TC-07 | Consensus level = none when count=0. | 1. Log in and call nearby endpoint at empty coordinate. 2. Inspect consensusLevel in response. | consensusLevel is none when there are zero matching reports. | Location has no matching report.
TC-08 | Consensus level mapping low/moderate/strong. | 1. Prepare nearby dataset with 1 then 2-3 then 4+ matching reports. 2. Call nearby endpoint after each setup. 3. Verify consensusLevel value. | Mapping is correct: 1->low, 2-3->moderate, 4+->strong. | Controlled test dataset available.
TC-09 | UI handles empty community feed gracefully. | 1. Log in with context having no matching data. 2. Open Community Flood Reports screen. 3. Observe UI after request completes. | HTTP 200 with empty array and UI empty state shown without crash. | No matching reports for selected scope.
Security & Access Control
TC-01 | Reject unauthenticated access to community feed endpoint. | 1. Sign out or remove access token. 2. Request GET /flood-reports/community. 3. Observe status and body. | HTTP 401 Unauthorized. No feed data is returned. | No valid token.
TC-02 | Reject unauthenticated access to nearby endpoint. | 1. Sign out or remove access token. 2. Send POST /flood-reports/nearby with valid body. 3. Observe status and body. | HTTP 401 Unauthorized. No nearby data is returned. | No valid token.

## FE-27
Feature | FE-27_Vote or Flag Flood Reports | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Voting Core Flow (Upvote/Downvote/Toggle)
TC-01 | Upvote a community flood report successfully. | 1. Log in with account A. 2. Open FE-26 community feed and select a Published report not owned by A. 3. Tap Upvote once. | Vote API returns success; score increases based on current vote state; UI highlights upvote state. | Authenticated user. Target report is Published.
TC-02 | Downvote a community flood report successfully. | 1. Log in with account A. 2. Open FE-26 community feed and select a Published report not owned by A. 3. Tap Downvote once. | Vote API returns success; score decreases based on current vote state; UI highlights downvote state. | Authenticated user. Target report is Published.
TC-03 | Replace existing vote from upvote to downvote. | 1. Log in with account A and upvote a target report. 2. Tap Downvote on the same report. 3. Inspect returned score and userVote. | Previous vote is replaced (not duplicated). Score adjusts with replacement logic; current user vote becomes -1. | User has existing upvote on target report.
TC-04 | Replace existing vote from downvote to upvote. | 1. Log in with account A and downvote a target report. 2. Tap Upvote on the same report. 3. Inspect returned score and userVote. | Previous vote is replaced (not duplicated). Score adjusts with replacement logic; current user vote becomes 1. | User has existing downvote on target report.
TC-05 | Toggle upvote off (remove vote) from FE behavior. | 1. Log in with account A and upvote a target report. 2. Tap Upvote again on the same report. 3. Observe UI and score after API response. | Vote is removed from current user context; score is reduced accordingly; UI returns to non-selected upvote state. | Current FE build supports toggling same vote to unvote.
TC-06 | Toggle downvote off (remove vote) from FE behavior. | 1. Log in with account A and downvote a target report. 2. Tap Downvote again on the same report. 3. Observe UI and score after API response. | Vote is removed from current user context; score is increased accordingly; UI returns to non-selected downvote state. | Current FE build supports toggling same vote to unvote.
TC-07 | Prevent voting on own report in UI. | 1. Log in with account A who is owner of a report. 2. Open own post card in community feed/profile. 3. Tap Upvote or Downvote. | UI blocks action and shows warning message; no vote API call changes score. | Post owner account available.
TC-08 | Block duplicate rapid vote submissions while request in-flight. | 1. Log in and open a report card. 2. Tap vote button repeatedly very quickly during loading state. 3. Inspect network requests and final UI score. | Only one effective vote operation is processed at a time; no duplicated inconsistent score updates. | Network logging enabled.
TC-09 | Vote response syncs UI score/userVote after optimistic update. | 1. Log in and trigger an upvote/downvote on a target report. 2. Compare temporary UI state with final API response payload. 3. Verify final rendered score and selected vote state. | Final UI state follows backend response fields (newScore, userVote). | Authenticated user. API response observable.
Score Recalculation & Auto-hide Rules
TC-01 | Initial report score baseline is 1 before voting. | 1. Create a fresh report via FE-25 flow. 2. Retrieve report details or feed item before any vote. 3. Check score field. | New report starts with score=1 as baseline. | Fresh report exists with no votes yet.
TC-02 | One vote per user per report (unique constraint) is enforced. | 1. Log in with account A and vote on report R. 2. Vote again on report R using account A with same or different vote type. 3. Inspect stored result via API response/feed. | System maintains a single effective vote per (ReportId,UserId); repeated voting updates existing record. | Account A and report R available.
TC-03 | Score recalculates correctly with mixed votes from multiple users. | 1. Prepare report R and have multiple users cast up/down votes. 2. Refresh feed/report detail after each vote sequence. 3. Verify resulting score against expected aggregate. | Report score matches baseline + net vote deltas according to business rules. | At least 3 test accounts available.
TC-04 | Report remains Published when score is above hide threshold. | 1. Prepare a report with score greater than -10. 2. Submit additional votes that keep score still > -10. 3. Refresh report status. | Status remains Published. | Controlled voting dataset ready.
TC-05 | Auto-hide report when score reaches <= -10. | 1. Prepare a report near threshold (for example score -9). 2. Submit one additional downvote that makes score <= -10. 3. Refresh report status. | Report status is updated to Hidden automatically. | Enough test users available for downvotes.
TC-06 | Hidden report is excluded from FE-26 community feed. | 1. Auto-hide a report by downvoting to threshold. 2. Open FE-26 feed with normal filters. 3. Search for the hidden report id. | Hidden report is not returned/displayed in community feed. | A report has been hidden successfully.
TC-07 | Vote update on invalid report id is handled safely. | 1. Log in with a valid account. 2. Call vote endpoint using a non-existing report id from FE/network tool. 3. Observe API and UI behavior. | Request returns error (4xx/5xx as designed); UI does not keep incorrect optimistic score. | Authenticated user. Non-existing report id prepared.
TC-08 | Vote endpoint returns expected minimum response data. | 1. Log in and cast a valid vote on a report. 2. Inspect API response payload. 3. Verify required fields. | Response contains at least report/user vote outcome fields (newScore, userVote); success/message are consistent. | Authenticated user. API inspection available.
TC-09 | Score/status changes become visible after feed refresh. | 1. Perform vote actions that change score (and optionally status). 2. Pull-to-refresh or reopen FE-26 feed. 3. Compare displayed score/status with latest backend state. | Feed reflects updated score/status without stale inconsistent values after refresh cycle. | Vote operation completed successfully.
Validation, Security & Error Handling
TC-01 | Reject unauthenticated vote request. | 1. Sign out or remove access token. 2. Attempt to vote on a report from FE or API tool. 3. Observe response status. | HTTP 401 Unauthorized (or auth failure). Vote is not applied. | No valid token.
TC-02 | Reject invalid voteType outside allowed values. | 1. Log in with valid account. 2. Send vote request with invalid voteType (e.g., 0 or 2) via API tool. 3. Inspect API response and report score. | Validation error returned; score remains unchanged. | Authenticated user. API test tool available.

## FE-35
Feature | FE-35_View Subscription Plans | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Plans Listing & UI Presentation
TC-01 | Load pricing plans list successfully (AllowAnonymous endpoint). | 1. Open Plans screen from app navigation. 2. Wait for request GET /api/v1/plans to complete. 3. Observe cards and table rendering. | HTTP 200 OK. Active plans are displayed with pricing cards and comparison information. | Network stable. Plans API has active data.
TC-02 | Display loading state while fetching plans. | 1. Open Plans screen on slow network/throttling mode. 2. Observe UI before GET /plans returns. | Loading indicator and loading text are shown until data is loaded. | Network throttling enabled.
TC-03 | Display retry error state when plans API fails. | 1. Simulate plans API failure (500/network error). 2. Open Plans screen. 3. Tap Retry button after error appears. | Error message + retry button are shown; tapping Retry triggers fetch again. | Can simulate API failure.
TC-04 | Display empty state when plans response is empty array. | 1. Mock GET /plans returns 200 with empty data array. 2. Open Plans screen and wait for render. | UI shows no-plans empty state message and does not crash. | API mock/seed supports empty data.
TC-05 | Plans are sorted in expected order Free -> Premium -> Monitor. | 1. Open Plans screen with all 3 plans available. 2. Inspect rendered card order top-to-bottom. | Cards appear in rank order FREE, PREMIUM, MONITOR. | All three plans are active in API data.
TC-06 | Pricing card displays key fields correctly. | 1. Open Plans screen. 2. Inspect each card for name/icon/price/CTA. 3. Cross-check values with API response. | Displayed plan name and monthly/yearly prices match API values. | API response captured for comparison.
TC-07 | Feature comparison table renders values from plan features. | 1. Open Plans screen. 2. Inspect comparison table rows (max areas, sms/email, priority, API access). 3. Compare with plan.features payload. | Table values and check/dash states map correctly from featureKey/featureValue. | Plans API includes features array.
TC-08 | Monthly-Yearly billing toggle updates displayed price. | 1. Open Plans screen with paid plans. 2. Observe default monthly price. 3. Switch to yearly and compare price fields. | Card price values switch between priceMonth and priceYear correctly. | At least one paid plan has distinct month/year price.
TC-09 | Pull-to-refresh updates plans and subscription data. | 1. Open Plans screen with existing loaded data. 2. Pull down to refresh. 3. Observe network calls and final UI values. | Refresh triggers refetch of plans and current subscription; UI updates with latest data. | Refresh gesture available on device.
Authentication, Current Plan & Action Buttons
TC-01 | Unauthenticated user can still view plans list. | 1. Sign out from app. 2. Open Plans screen. 3. Wait for plans load. | Plans are displayed without requiring login; no current-plan highlight. | User is logged out.
TC-02 | Unauthenticated current subscription request 401 does not break screen. | 1. Ensure user is logged out. 2. Open Plans screen and monitor GET /plan/subscription/current. 3. Observe resulting UI behavior. | Subscription 401 is handled gracefully; plans still display normally without crash. | Logged-out state and network inspector available.
TC-03 | Authenticated user current plan is highlighted as in-use. | 1. Log in with account having active subscription (e.g., Premium). 2. Open Plans screen and wait for subscription data. 3. Check badge/button state on matching card. | Current subscription card is highlighted with in-use state; current action is disabled. | User account has active subscription.
TC-04 | Action label for higher tier is Upgrade/Nang cap. | 1. Log in with FREE or lower-tier account. 2. Open Plans screen and locate higher-tier card. 3. Inspect action button label. | Higher-tier plan action shows upgrade intent and is clickable. | Authenticated account with lower current tier.
TC-05 | Action label for lower tier is Downgrade/Ha cap. | 1. Log in with Premium or Monitor account. 2. Open Plans screen and inspect lower-tier card action. 3. Tap the lower-tier action button. | Button indicates downgrade intent and opens downgrade confirmation flow. | Authenticated account on higher-tier subscription.
TC-06 | Tap current plan button performs no change. | 1. Log in with active subscription. 2. Open Plans screen and tap button on current plan card. 3. Observe behavior and network activity. | Current plan action remains disabled/no-op; no payment or downgrade API call fired. | Current subscription data loaded.
TC-07 | Unauthenticated tap on paid plan prompts login flow. | 1. Sign out and open Plans screen. 2. Tap action button on Premium/Monitor card. 3. In prompt, choose Login action. | Login-required alert appears and navigates user to login when confirmed. | Logged-out user and navigation enabled.
TC-08 | Upgrade flow opens duration modal and creates payment link. | 1. Log in with eligible account for upgrade. 2. Tap upgrade action and select duration in modal. 3. Confirm payment creation. | Payment link API is called, then app navigates to payment processing screen with paymentUrl/orderCode. | Payment service available; account eligible for upgrade.
TC-09 | Downgrade-to-free flow confirms and updates subscription. | 1. Log in with paid subscription account. 2. Tap downgrade action to FREE and confirm dialog. 3. Wait for API response and UI refresh. | Downgrade API succeeds, current subscription query is invalidated/refreshed, and success message is shown. | Paid account with permission to downgrade.
Subscription Errors & Edge Cases
TC-01 | Subscription API 500 shows warning path but plans remain visible. | 1. Log in with valid account. 2. Mock GET /plan/subscription/current returns 500. 3. Open Plans screen. | Plans list still renders from /plans data; subscription failure does not block viewing plans. | Can simulate subscription endpoint failure.
TC-02 | Expired/invalid token on subscription fetch handled safely. | 1. Use expired token session and open Plans screen. 2. Observe subscription request result. 3. Inspect UI and navigation behavior. | Unauthorized subscription response is handled; app remains stable and does not corrupt plans display. | Session with expired token available.

## FE-36
Feature | FE-36_Upgrade / Downgrade Subscription | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Upgrade Flow - Payment Creation & Redirect
TC-01 | Open duration selection modal from Upgrade action. | 1. Log in with account eligible for paid upgrade. 2. Open Plans screen and tap Upgrade on PREMIUM or MONITOR card. 3. Observe bottom-sheet/modal content. | Duration selection modal opens with options 1/3/6/12 months and displays plan/monthly price. | Authenticated user. Eligible plan available.
TC-02 | Create payment link successfully with valid payload. | 1. From duration modal, choose a valid duration. 2. Tap Continue or Proceed to Payment. 3. Inspect request payload and API response. | POST /api/v1/payment/create succeeds and returns paymentUrl + orderCode. | User authenticated. Backend payment service available.
TC-03 | Navigate to processing screen after payment link creation. | 1. Trigger successful create payment link flow. 2. Observe app navigation immediately after API response. | App navigates to /payment/processing and passes paymentUrl + orderCode params. | Successful create payment response exists.
TC-04 | Processing screen auto-opens PayOS checkout URL. | 1. Enter /payment/processing with valid paymentUrl param. 2. Wait for auto-open logic to run. | System browser or web checkout opens PayOS URL automatically. | Valid paymentUrl generated from backend.
TC-05 | Processing screen shows timeout error when redirect cannot open in 5s. | 1. Enter /payment/processing with invalid or unopenable paymentUrl. 2. Wait at least 5 seconds. 3. Observe state transition. | Error state appears with retry and back-to-plans actions. | Can simulate URL open failure.
TC-06 | Retry button on processing screen attempts open payment again. | 1. Reach processing error state. 2. Tap Retry button once. 3. Observe browser open attempt and UI state. | App retries opening payment URL and clears error if open succeeds. | Processing screen currently in error state.
TC-07 | Back action from processing error returns to plans selection. | 1. Reach processing error state. 2. Tap back button to return plan selection. 3. Observe navigation destination. | User is redirected back to plans screen for reselection. | Processing screen in error state.
TC-08 | Validation error on invalid duration is handled gracefully. | 1. Simulate create-payment request with invalid durationMonths via API tool. 2. Trigger payment creation flow. 3. Observe UI error handling. | Validation error is shown and user remains on selection flow without app crash. | Ability to mock invalid request or backend validation response.
TC-09 | Unauthorized upgrade request redirects user to login path. | 1. Expire or remove auth token before confirming upgrade. 2. Trigger create payment request. 3. Observe response handling and navigation. | 401 is handled; user is asked or redirected to login flow. | Expired or missing token session.
Payment Callback, Polling & Result States
TC-01 | Success page starts polling payment status by orderCode. | 1. Open /payment/success with valid orderCode query param. 2. Monitor network calls for payment status endpoint. 3. Observe polling interval. | GET /api/v1/payment/status/{orderCode} starts immediately and repeats every about 3 seconds. | Valid orderCode available.
TC-02 | Pending status keeps spinner state and continues polling. | 1. Mock payment status returns pending on initial polls. 2. Stay on /payment/success for multiple intervals. | UI remains in pending/loading confirmation state while polling continues. | Payment status endpoint returns pending.
TC-03 | Paid status stops polling and shows success actions. | 1. Start with pending status then switch API response to paid. 2. Observe UI update on next poll. 3. Check available action buttons. | Polling stops, success state is shown, and action to view current plans appears. | Order transitions to paid state.
TC-04 | Cancelled status maps to cancelled result screen. | 1. Open success page with orderCode whose status is cancelled. 2. Wait for poll response. | UI shows cancelled state and back-to-plans action. | Existing order with cancelled status.
TC-05 | Failed status maps to failed result screen. | 1. Open success page with orderCode whose status is failed. 2. Wait for poll response. | UI shows failed state and allows return to plans. | Existing order with failed status.
TC-06 | Polling timeout after max attempts shows timeout state. | 1. Keep payment status pending continuously. 2. Wait until max polling attempts are reached. 3. Observe final state. | After timeout threshold, UI shows processing-timeout message and provides navigation action. | Can mock pending for full timeout period.
TC-07 | Success page with missing or invalid orderCode remains stable. | 1. Open /payment/success without orderCode or with invalid orderCode. 2. Observe rendered state and actions. | Screen stays stable and still allows user to return to plans. | Route is accessible directly.
TC-08 | Payment cancel page displays cancellation message and safe fallback. | 1. Open /payment/cancel via callback or direct route. 2. Verify message and action button. 3. Tap return button. | Cancellation message is shown; tapping action redirects to plans screen. | Cancel route available.
TC-09 | Network errors during polling do not crash and still timeout safely. | 1. Open success page with valid orderCode. 2. Simulate intermittent network failures on polling calls. 3. Observe state over time. | App tolerates polling errors, keeps retrying, then transitions to timeout after max attempts. | Can simulate network failure on status endpoint.
Downgrade Flow (Subscribe FREE)
TC-01 | Open downgrade confirmation dialog when choosing FREE from paid plan. | 1. Log in with paid subscription account. 2. Open Plans screen and tap Downgrade on FREE plan card. 3. Observe dialog content. | Downgrade confirmation dialog opens with warning text and cancel/confirm buttons. | Account currently on Premium or Monitor.
TC-02 | Cancel downgrade closes dialog without plan changes. | 1. Open downgrade confirmation dialog. 2. Tap Cancel. 3. Recheck current subscription info. | Dialog closes and current subscription remains unchanged. | Downgrade dialog is visible.
TC-03 | Confirm downgrade calls subscribe FREE and updates subscription. | 1. Open downgrade dialog and tap Confirm. 2. Monitor POST /api/v1/plan/subscription/subscribe payload. 3. Wait for response and subscription refresh. | API call succeeds with planCode=FREE; subscription query refreshes and UI reflects Free plan as current. | Paid account allowed to downgrade.
TC-04 | Downgrade failure shows error and keeps current plan. | 1. Trigger downgrade API failure (400 or 500). 2. Confirm downgrade in dialog. 3. Observe error feedback and plan state. | Error is shown to user; no unintended plan switch occurs. | Can simulate backend downgrade failure.
TC-05 | Unauthorized downgrade request is handled securely. | 1. Expire or remove token before confirming downgrade. 2. Trigger downgrade request. 3. Observe response and navigation handling. | 401 unauthorized is handled; downgrade is not applied and user is guided to re-authenticate. | Invalid token session available.

## FE-37
Feature | FE-37_Cancel Subscription | [13 empty] | Passed
Test requirement | [14 empty] | Failed
Number of TCs | [14 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1
Round 2
Round 3
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Current Subscription View & Cancel Entry Conditions
TC-01 | Load current subscription details successfully. | 1. Sign in with a valid account. 2. Open the Current Plan screen. 3. Verify subscription details are displayed. | Subscription details are displayed including tier, status, dates, channels, delay and retries. | Authenticated user with available subscription data.
TC-02 | Show cancel button only for paid tiers. | 1. Open Current Plan with a paid account. 2. Check the action area at the bottom. 3. Verify the Cancel button is visible only for paid plans. | Cancel subscription button appears only for paid plans and is hidden for FREE tier. | Two test accounts: paid and free.
TC-03 | Free-plan user cannot start cancel flow. | 1. Sign in with a Free plan account. 2. Open Current Plan screen. 3. Verify there is no Cancel flow to start. | No cancel action is available, so cancel flow cannot be started from UI. | User currently on free tier.
TC-04 | Handle load error state for current subscription. | 1. Simulate a load error for current subscription. 2. Open Current Plan screen. 3. Verify safe error UI is shown. | Error state message is shown safely with back navigation option; app does not crash. | Can mock subscription endpoint failure.
TC-05 | Refresh current subscription after manual re-open/re-enter screen. | 1. Open Current Plan and note current values. 2. Leave the screen and open it again. 3. Verify latest subscription values are shown. | Latest subscription information is shown after re-entering, reflecting current server state. | Subscription can be changed from backend/test setup.
TC-06 | Cancel button style is destructive and clearly distinguishable. | 1. Open Current Plan with a paid account. 2. Check the Cancel action style. 3. Verify it looks like a destructive action. | Cancel action uses danger styling and clear destructive affordance. | Paid subscription account.
TC-07 | Open cancel dialog from paid subscription screen. | 1. Open Current Plan with a paid account. 2. Tap Cancel Subscription. 3. Verify cancel dialog is opened. | Cancel dialog opens and overlays screen correctly. | Paid subscription account.
TC-08 | Cancel dialog can be closed without side effects. | 1. Open cancel dialog. 2. Tap Keep current plan / close action. 3. Verify no subscription change happens. | Dialog closes and subscription remains unchanged. | Cancel dialog currently open.
TC-09 | Cancel dialog reason input accepts optional text. | 1. Open cancel dialog. 2. Type text into the optional reason field. 3. Verify input is accepted and stays visible. | Reason text is accepted and retained for submit action; no validation required for empty input. | Cancel dialog open for paid user.
Cancel API Flow, Success Handling & State Update
TC-01 | Submit cancel request successfully with reason. | 1. Open cancel dialog for a paid plan. 2. Enter a reason and tap Confirm cancel. 3. Verify cancel request succeeds. | API request succeeds and includes cancelReason in request body. | Paid subscription account and backend available.
TC-02 | Submit cancel request successfully without reason. | 1. Open cancel dialog for a paid plan. 2. Leave reason empty and tap Confirm cancel. 3. Verify cancel still succeeds. | Cancellation still succeeds when reason is omitted (optional field). | Paid subscription account.
TC-03 | Show loading state while cancelling subscription. | 1. Open cancel dialog and tap Confirm cancel. 2. Observe button/dialog during processing. 3. Verify loading state prevents duplicate submit. | Loading indicator appears and duplicate submits are prevented while request is in progress. | Network response delay visible.
TC-04 | Successful cancel invalidates and refreshes current subscription query. | 1. Complete a successful cancel action. 2. Re-open subscription info. 3. Verify it refreshes to Free plan state. | Subscription state refreshes and reflects FREE tier after cancellation. | Cancel API success response.
TC-05 | Successful cancel shows success message then navigates to plans. | 1. Complete a successful cancel action. 2. Check success feedback message. 3. Verify app navigates back to plans. | User sees success feedback and is redirected to plans page. | Cancel API success response.
TC-06 | Response data contains cancelled subscription metadata. | 1. Run a successful cancel action. 2. Inspect response data in test tools. 3. Verify cancel metadata fields are present. | Response includes subscriptionId, planName, previousTier, cancelledAt, and cancelReason when provided. | Backend returns cancel metadata.
TC-07 | Post-cancel plan capabilities are downgraded in UI. | 1. Cancel a paid subscription successfully. 2. Open related plan screens again. 3. Verify paid-only capabilities are no longer active. | User appears on Free plan and paid-tier capabilities are no longer available in UI. | Cancellation completed successfully.
TC-08 | Attempt repeat cancel after already free is blocked by server. | 1. Use an account already on Free plan. 2. Try cancel action again in test flow. 3. Verify system blocks repeated cancel. | Server returns business error for free plan state; UI does not break. | Account already in free tier.
TC-09 | Cancel from MONITOR tier returns proper previousTier. | 1. Use an account currently on Monitor plan. 2. Confirm cancel action. 3. Verify previous tier is recorded correctly. | Cancel response previousTier correctly identifies Monitor tier. | MONITOR subscription account available.
Error Handling, Security & Edge Cases
TC-01 | Unauthorized cancel request is handled securely. | 1. Use an expired or missing token session. 2. Try to confirm subscription cancel. 3. Verify unauthorized handling is safe. | 401 response is handled safely and user is redirected/re-auth prompted by auth flow. | Invalid token session.
TC-02 | Server 500 during cancel keeps dialog usable with error feedback. | 1. Simulate server error during cancel. 2. Confirm cancel in dialog. 3. Verify error message appears and dialog stays usable. | Error message is shown; dialog remains recoverable for retry or close. | Can simulate server error.
TC-03 | Network failure during cancel does not corrupt subscription state. | 1. Disable network before confirming cancel. 2. Tap Confirm cancel. 3. Verify plan is unchanged and error is shown. | Connection error is shown and current subscription remains unchanged. | Can toggle network state.
TC-04 | Cancel endpoint not found or invalid route returns safe failure. | 1. Simulate invalid route or not-found response on cancel. 2. Trigger cancel action. 3. Verify failure message is shown with no false success. | UI shows failure message and avoids false-success transition. | Can mock endpoint response 404.
TC-05 | Dialog and loading states clean up correctly after failure. | 1. Trigger one failed cancel attempt. 2. Close and reopen cancel dialog. 3. Verify dialog/loading state is reset correctly. | Dialog state resets correctly; user can retry without stale loading lock. | One failed cancel attempt performed.